## Overview
AI-Based Knowledge Retrieval Platform with Query Resolution System
Agile / Scrum Internship Artifact — based on uploaded project guide and source tree
Milestone | Scope | Status | Status | Count
M1 | Core RAG Platform | Completed | Completed | 2
M2 | Multi-Agent Query Resolution | Completed | Validated | 2
M3 | Conversational Experience, Voice, Transparency & Auth | Validated | Integrated / Partially Validated | 1
M4 | Analytics, Knowledge Gaps & User-Specific Knowledge Base | Integrated / Partially Validated
Artifact | Purpose
Product Backlog | User stories and acceptance criteria
Sprint Backlog | Implementation tasks mapped to M1–M4
Stand-up / Retrospection | Execution updates and sprint learning
Documentation note | Value
Dates | Not supplied in the project source; date fields are left blank for team/mentor entry.
Assignee / Team Member | Individual contribution: OCR pipeline and user query knowledge retrieval.
Status basis | Completed/Validated labels are taken from PROJECT_GUIDE.md; no additional completion claims were invented.
Defects | Only documented development issues are included in the separate Defect Tracker.

## Product Backlog
Product Backlog
SL No | US ID | User Story Description | MOSCOW | Priority | Category | Milestone | Acceptance Criteria | Status
1 | US-01 | As a user, I want to upload PDF, DOCX, TXT, CSV, JPG, JPEG and PNG documents so they become searchable knowledge. | Must | High | Document Ingestion | M1 | Supported formats are accepted and processing status is tracked. | Completed
2 | US-02 | As a user, I want uploaded content extracted, chunked and embedded automatically, including scanned PDFs and image-based content. | Must | High | RAG | M1 | Native extraction/OCR, chunking and SentenceTransformer embeddings complete successfully; OCR is used where native text extraction is not available. | Completed
3 | US-03 | As a user, I want document chunks and embeddings stored for semantic retrieval. | Must | High | Vector Store | M1 | Chunks and embeddings are persisted in ChromaDB with metadata. | Completed
4 | US-04 | As a user, I want to ask natural-language questions about my knowledge base, including OCR-extracted content. | Must | High | Query | M1 | Relevant context is retrieved and a grounded response is generated; relevant OCR-extracted content can also be retrieved. | Completed
5 | US-05 | As a user, I want my query normalized, classified and understood before retrieval. | Must | High | Query Understanding | M2 | Normalization, entity/keyword extraction and classification are available. | Completed
6 | US-06 | As a user, I want the system to route each query to the appropriate processing path. | Must | High | Orchestration | M2 | LangGraph routing selects general-knowledge, clarification or RAG paths as appropriate. | Completed
7 | US-07 | As a user, I want retrieved candidates reranked and low-confidence results filtered. | Must | High | Retrieval | M2 | Semantic/exact candidates are merged, reranked and filtered. | Completed
8 | US-08 | As a user, I want answers grounded in retrieved evidence with sources and confidence. | Must | High | Response Generation | M2 | Knowledge-base responses provide citations/source attribution and confidence information. | Completed
9 | US-09 | As a user, I want ambiguous questions clarified before the system answers. | Must | High | Clarification | M3 | A targeted clarification question is generated and follow-up input refines the query. | Validated
10 | US-10 | As a user, I want follow-up questions to use previous conversation context. | Must | High | Conversation Memory | M3 | conversation_id is persisted and prior turns are loaded for contextual follow-ups. | Validated
11 | US-11 | As a user, I want browser voice input and text-to-speech. | Should | Medium | Voice | M3 | Web Speech API transcript enters the normal /query flow and Speech Synthesis reads responses. | Validated
12 | US-12 | As a user, I want to inspect citations, sources, confidence and retrieved context. | Should | Medium | Transparency | M3 | Context Inspector and citation display expose retrieval evidence. | Validated
13 | US-13 | As a user, I want secure sign-in and access only to my own conversations and workspace. | Must | High | Authentication | M3 | JWT authentication and user ownership/isolation are enforced. | Validated
14 | US-14 | As a user, I want query analytics and knowledge-gap detection for recurring unanswered/low-confidence topics. | Must | High | Analytics & Knowledge Gaps | M4 | Query telemetry, query types, semantic themes and gap detection are available. | Integrated
15 | US-15 | As a user, I want a private knowledge base isolated from other users. | Must | High | User-Specific Knowledge Base | M4 | Authenticated upload/list/search/delete and user-scoped ChromaDB retrieval are enforced. | Validated
16 | US-16 | As an administrator, I want system-wide user, document and analytics visibility. | Should | Medium | Admin Dashboard Backend | M4 | Admin overview, users, documents, analytics and delete endpoints are implemented and secured. | Backend Integrated

## Sprint Backlog
Sprint Backlog — M1 to M4
SL No | Sprint # | Sprint | Task ID | Task Description | US ID | Assignee | Priority | Status | Sprint Start Date | Sprint End Date | Task Start Date | Task Completion Date | Impediments | Action Taken
1 | 1 | M1 | M1-T01 | Implement multi-format document upload and processing-status handling. | US-01 | Project Team | High | Completed
2 | 1 | M1 | M1-T02 | Implement native PDF/DOCX/TXT/CSV extraction and OCR fallback for scanned/image content. | US-02 | Project Team | High | Completed
3 | 1 | M1 | M1-T03 | Implement recursive text chunking and SentenceTransformer embedding generation. | US-02 | Project Team | High | Completed
4 | 1 | M1 | M1-T04 | Persist chunks/embeddings in ChromaDB and document metadata/status in PostgreSQL. | US-03 | Project Team | High | Completed
5 | 1 | M1 | M1-T05 | Implement baseline semantic retrieval and grounded answer generation. | US-04 | Project Team | High | Completed
6 | 2 | M2 | M2-T01 | Implement Query Understanding Agent for normalization, entity/keyword extraction and classification. | US-05 | Project Team | High | Completed
7 | 2 | M2 | M2-T02 | Implement deterministic LangGraph query routing. | US-06 | Project Team | High | Completed
8 | 2 | M2 | M2-T03 | Enhance retrieval with semantic search, optional exact search, candidate merging and reranking. | US-07 | Project Team | High | Completed
9 | 2 | M2 | M2-T04 | Implement Response Generation Agent with source attribution and confidence handling. | US-08 | Project Team | High | Completed
10 | 3 | M3 | M3-T01 | Implement Clarification Agent and query refinement path for ambiguous questions. | US-09 | Project Team | High | Validated
11 | 3 | M3 | M3-T02 | Implement PostgreSQL-backed Conversation Memory using conversation_id. | US-10 | Project Team | High | Validated
12 | 3 | M3 | M3-T03 | Integrate browser Web Speech API input and Speech Synthesis output through /query. | US-11 | Project Team | Medium | Validated
13 | 3 | M3 | M3-T04 | Implement response transparency, citations, source details, relevance/confidence and context inspection. | US-12 | Project Team | Medium | Validated
14 | 3 | M3 | M3-T05 | Implement JWT authentication, session restore, logout and user-specific conversation ownership. | US-13 | Project Team | High | Validated
15 | 4 | M4 | M4-T01 | Persist query analytics including query type, answer status, confidence and response time. | US-14 | Project Team | High | Integrated
16 | 4 | M4 | M4-T02 | Implement domain-agnostic common query-theme detection using analytics-only embeddings. | US-14 | Project Team | Medium | Integrated
17 | 4 | M4 | M4-T03 | Implement knowledge-gap detection for zero retrieval, low-confidence and repeated gaps. | US-14 | Project Team | High | Integrated
18 | 4 | M4 | M4-T04 | Implement authenticated user-specific knowledge-base document lifecycle and user-scoped ChromaDB retrieval. | US-15 | Project Team | High | Validated
19 | 4 | M4 | M4-T05 | Connect Analytics and Knowledge Gap dashboards to real backend data. | US-14 | Project Team | Medium | Validated
20 | 4 | M4 | M4-T06 | Implement and locally test Admin backend overview, users, documents and analytics endpoints. | US-16 | Project Team | Medium | Backend Integrated

## Stand-up Meeting
Sprint | Milestone | My Work / Contribution | Status | Impediments / Notes | Action Taken
1 | M1 - Core RAG Platform | Worked on scanned PDF/image document processing using the OCR pipeline; integrated extracted text into the document processing flow and supported knowledge storage/retrieval. | Completed | OCR processing and scanned-document handling required validation. | Tested OCR extraction and connected the extracted content with the RAG ingestion flow.
1 | M1 - Core RAG Platform | Worked on ChromaDB knowledge storage and retrieval, including storing document chunks/embeddings and supporting user-specific knowledge retrieval. | Completed | Needed to maintain correct document metadata and retrieval scope. | Validated chunk storage and retrieval flow with the project knowledge base.
2 | M2 - Multi-Agent Query Resolution | Worked on LLM calls for response generation and on connecting retrieved context with the LLM-based answer generation flow. | Completed | Retrieved context had to be passed consistently to the LLM for grounded responses. | Integrated and tested the LLM call with the retrieval/response flow.
2 | M2 - Multi-Agent Query Resolution | Worked on workflow orchestration, including connecting query-processing components and routing the query through the appropriate processing path. | Completed | Multiple processing components had to exchange the correct query and context state. | Tested the end-to-end orchestration flow and component transitions.
3 | M3 - Conversational Experience, Voice, Transparency & Auth | Contributed to the speech/voice interaction flow by connecting speech input/output with the normal query-processing workflow. | Validated | Voice interaction needed to remain consistent with the existing query flow. | Integrated and tested speech interaction with query processing.
3 | M3 - Conversational Experience, Voice, Transparency & Auth | Supported integration testing of the LLM, retrieval and orchestration components within the conversational query flow. | Validated | Maintaining context across the conversational flow required end-to-end testing. | Validated the integrated query-to-response flow.
4 | M4 - Analytics, Knowledge Gaps & User-Specific Knowledge Base | Worked on authenticated user-specific knowledge-base handling and user-scoped ChromaDB retrieval so that knowledge is isolated by user. | Validated | User-level isolation had to be maintained during upload, search and retrieval. | Tested user-scoped document retrieval and knowledge-base access.
4 | M4 - Analytics, Knowledge Gaps & User-Specific Knowledge Base | Supported integration and validation of the knowledge retrieval flow across OCR content, ChromaDB retrieval, LLM response generation and workflow orchestration. | Integrated / Validated | End-to-end integration required checking each stage of the pipeline. | Performed end-to-end validation and fixed integration issues found during testing.

## Retrospection
Milestone | What Went Well | Challenges / Impediments | What Could Be Improved | My Contribution
M1 - Core RAG Platform | Document ingestion, OCR, chunking, embeddings, ChromaDB storage and baseline retrieval were brought together into the core RAG flow. | Scanned documents and image-based content required reliable OCR extraction and validation before indexing. | Improve OCR handling for difficult scans and continue optimizing ingestion and retrieval performance. | Contributed to the OCR pipeline and connected OCR-extracted content with ChromaDB-based knowledge retrieval.
M2 - Multi-Agent Query Resolution | Query understanding, retrieval, response generation and LangGraph-based routing were integrated into the multi-agent flow. | The workflow had to maintain the correct query/context state between components, and LLM responses needed relevant retrieved context. | Improve orchestration robustness and response consistency across different query paths. | Contributed to LLM calls/response generation and workflow orchestration, including integration and testing of the query flow.
M3 - Conversational Experience, Voice, Transparency & Auth | Conversation, voice interaction, response transparency and authentication features were integrated into the user experience. | Speech interaction and conversational flow had to work consistently with the existing query pipeline. | Improve voice interaction reliability and further streamline the conversational workflow. | Contributed to the speech/voice interaction component and its integration with the normal query-processing flow.
M4 - Analytics, Knowledge Gaps & User-Specific Knowledge Base | Analytics and knowledge-base features were integrated, including user-specific knowledge handling and scoped retrieval. | Maintaining user-level isolation in ChromaDB while supporting upload/search/retrieval required careful validation. | Further strengthen user-scoped retrieval validation and improve integration between knowledge-base and analytics features. | Contributed to user-specific ChromaDB knowledge management and validation of user-scoped retrieval.
Overall Sprint Learning | The major components—OCR, vector storage, retrieval, LLM calls, orchestration and voice interaction—were progressively integrated as part of the team project. | Integration across multiple components required repeated end-to-end testing and debugging. | Use more automated integration tests and clearer component-level validation checkpoints. | Worked across OCR, user-specific ChromaDB knowledge, LLM integration, workflow orchestration and speech/voice interaction while collaborating with the project team.